## 📋 Cover
TRAGAD SONI COMMUNITY
Website Development · Complete Project Roadmap
— Samaj · Sewa · Sangathan —
Document | Tragad Soni Community Website — Full Roadmap & Feature Spec
Version | 1.0 — May 2026
Scope | Planning · Design · Dev · Member Portal · Trade Directory · Education · Health · Matrimony
Audience | Samaj Trustees · Committee Members · Developers · Community Leaders
Language | English (Gujarati labels in portal)
Location | Surat, Gujarat, India
PREPARED BY
Name | Milan · SNTL 84
Role | AI Workflow Professional · Surat, India
Expertise | AI Systems ¦ Full-Stack Builds ¦ Supply Chain Business Intelligence
Tagline | Automate What's Costing You Money. Built for founders who move fast and waste nothing.
Website | https://desidevloper.com/
WhatsApp | https://wa.me/919727413309
LinkedIn | https://www.linkedin.com/in/sntl2784
GitHub | https://github.com/SNTL84
🚀 Follow Milan for AI Workflows, Full-Stack Dev & Supply Chain Intelligence
SHEETS IN THIS WORKBOOK
📋 Cover | Credits, document info, sheet index
🗺️ Master Roadmap | All 5 phases, milestones, timeline, owners
⚙️ Tech Stack | Recommended technologies, hosting, CMS, tools
👤 Member Portal | Full feature list: registration, directory, profiles, family
🏠 Family Reg. | Family registration form spec & data fields
🏪 Trade Directory | Business/trade listing feature spec
🎓 Study Alignment | Education, scholarships, study support features
🏫 School Section | School listings, admissions, tutors, results
🏥 Healthcare | Doctors, hospitals, health camps, wellness
💍 Matrimony | Matrimony section feature spec & profile fields
📅 Phase Detail | Detailed task tracker for all 5 phases

## 🗺️ Master Roadmap
TRAGAD SONI COMMUNITY WEBSITE — MASTER ROADMAP
Phase | Task / Deliverable | Description | Timeline | Owner | Priority | Status | Milestone
Phase 1 Planning | Define website goals | List features: directory, events, matrimony, donations, news, gallery | Week 1 | Trustee Committee | 🔴 High | ⬜ To Do
| Stakeholder interviews | Collect input from community leaders, youth group, elderly members | Week 1 | Project Lead | 🔴 High | ⬜ To Do
| Competitor research | Review 3–5 similar samaj websites for inspiration and gap analysis | Week 1 | Researcher | 🟡 Medium | ⬜ To Do
| Tech stack decision | Choose: WordPress vs custom (React+Node) — see Tech Stack sheet | Week 2 | Developer | 🔴 High | ⬜ To Do
| Domain & hosting setup | Register tragadsoni.org/.com, set up hosting, email domain | Week 2 | Admin | 🔴 High | ⬜ To Do | ✅ M1 Complete
Phase 2 Design | Sitemap creation | Map all pages: Home, About, Members, Events, Gallery, Contact etc. | Week 3 | UX Designer | 🔴 High | ⬜ To Do
| Wireframes (mobile-first) | Wireframe each page, prioritise mobile layout for Gujarat users | Week 3 | UX Designer | 🔴 High | ⬜ To Do
| Branding & logo | Design logo, choose colors, fonts reflecting Soni cultural identity | Week 4 | Designer | 🔴 High | ⬜ To Do
| Gujarati language support | Plan bilingual UI: Gujarati script + English toggle | Week 4 | Developer | 🟡 Medium | ⬜ To Do
| Design approval | Review & sign-off by samaj committee on all designs | Week 5 | Committee | 🔴 High | ⬜ To Do | ✅ M2 Complete
Phase 3 Development | Core pages development | Homepage, About, History, Trust/Committee, Contact, Donation page | Week 6–7 | Developer | 🔴 High | ⬜ To Do
| Member registration portal | Signup, login, profile, family tree — see Member Portal sheet | Week 7–8 | Developer | 🔴 High | ⬜ To Do
| Member directory & search | Search by name, city, profession, family; privacy controls | Week 8–9 | Developer | 🔴 High | ⬜ To Do
| Family registration module | Family unit registration with head-of-family, members, tree | Week 9 | Developer | 🔴 High | ⬜ To Do
| Events calendar | Post events, RSVP, reminders, past events archive | Week 9–10 | Developer | 🟡 Medium | ⬜ To Do
| Photo & video gallery | Albums by event/year, upload by admin, lightbox viewer | Week 10 | Developer | 🟡 Medium | ⬜ To Do
| Trade/business directory | Member business listings with category, location, contact | Week 10–11 | Developer | 🟡 Medium | ⬜ To Do
| Education & school section | Scholarships, school listings, tutor directory, study groups | Week 11 | Developer | 🟡 Medium | ⬜ To Do
| Healthcare directory | Doctors, hospitals, health camps, wellness resources | Week 11–12 | Developer | 🟡 Medium | ⬜ To Do
| Matrimony section | Profile creation, match search, privacy-first design | Week 12 | Developer | 🔴 High | ⬜ To Do
| Admin panel | CMS for trustees: post news, manage members, approve listings | Week 12 | Developer | 🔴 High | ⬜ To Do | ✅ M3 Beta Ready
Phase 4 Testing | Cross-device QA testing | Test on Android, iOS, desktop — Chrome, Safari, Firefox | Week 13 | QA Tester | 🔴 High | ⬜ To Do
| Performance optimisation | Page load <3s, image compression, CDN, lazy loading | Week 13 | Developer | 🔴 High | ⬜ To Do
| Security audit | SSL, HTTPS, data encryption, member data privacy (PDPA) | Week 14 | Developer | 🔴 High | ⬜ To Do
| Content entry | Enter samaj history, trustee profiles, initial 50 member records | Week 14 | Content Team | 🟡 Medium | ⬜ To Do
| Pilot with 30 members | Closed beta — collect feedback, fix usability issues | Week 15 | Project Lead | 🔴 High | ⬜ To Do | ✅ M4 Launch-Ready
Phase 5 Launch | Official launch event | Announce at samaj gathering; demo the website live | Week 16 | Trustees | 🔴 High | ⬜ To Do
| WhatsApp / social campaign | Broadcast registration link to all community WhatsApp groups | Week 16 | Volunteers | 🔴 High | ⬜ To Do
| Member onboarding drive | Help elderly members register; appoint city-level coordinators | Week 16–18 | Coordinators | 🔴 High | ⬜ To Do
| Admin team training | Train 3–4 admins on posting news, approving members, managing events | Week 17 | Developer | 🟡 Medium | ⬜ To Do
| Monthly content schedule | Plan monthly news, events, gallery updates, notices | Ongoing | Admin Team | 🟡 Medium | ⬜ To Do
| Quarterly feature review | Collect feedback; plan new features every 3 months | Ongoing | Committee | 🟢 Normal | ⬜ To Do | ✅ M5 Live & Growing

## ⚙️ Tech Stack
TRAGAD SONI — RECOMMENDED TECH STACK
Layer | Technology | Why This Choice | Cost / Month | Skill Level | Priority
Frontend | React.js + Next.js | Fast, SEO-friendly, supports Gujarati Unicode, mobile-first | Free / Open Source | Mid-level dev | 🔴 High
Frontend | Tailwind CSS | Rapid styling, responsive, minimal CSS code | Free | Any dev | 🔴 High
Frontend | i18next (translation) | Easy English ↔ Gujarati language toggle | Free | Mid-level dev | 🔴 High
Backend | Node.js + Express | Fast APIs, large community, good for real-time features | Free | Mid-level dev | 🔴 High
Backend (Alt) | WordPress + Elementor | Easier for non-technical admins; large plugin ecosystem | ₹500–₹2,000/mo | Non-technical | 🟡 Alt Option
Database | PostgreSQL | Reliable relational DB for members, families, profiles | Free (self-hosted) | Mid-level dev | 🔴 High
Database (Alt) | MySQL | Simpler alternative; widely supported with WordPress | Free | Any dev | 🟡 Alt Option
Auth | Firebase Auth or Auth0 | Secure login, OTP via phone/email, Google sign-in | Free tier avail. | Mid-level dev | 🔴 High
Hosting | Vercel (Frontend) | Free tier, auto-deploy from GitHub, CDN built-in | Free – ₹1,500/mo | Any dev | 🔴 High
Hosting | DigitalOcean Droplet | ₹900/mo VPS for backend + DB; full control | ₹900–₹1,800/mo | Senior dev | 🔴 High
Hosting (Alt) | Hostinger / Bluehost India | WordPress hosting; easy cPanel; good India support | ₹200–₹700/mo | Non-technical | 🟡 Alt Option
Storage | AWS S3 / Cloudflare R2 | Gallery photos, documents; cheap bulk storage | ₹100–₹500/mo | Mid-level dev | 🔴 High
Email | Zoho Mail (Free) | Professional @tragadsoni.org emails for committee | Free (5 users) | Non-technical | 🟡 Medium
Notifications | WhatsApp Business API | Send event reminders, notices to members via WhatsApp | ₹0.40/message | Developer | 🟡 Medium
Notifications | Firebase Push + Email | Browser push notifications + transactional email | Free tier avail. | Developer | 🟡 Medium
Search | Algolia / MeiliSearch | Fast member & business directory search with filters | Free tier avail. | Developer | 🟡 Medium
Maps | Google Maps API | Show member/business locations, event venues on map | Free (limited) | Developer | 🟢 Low
Analytics | Google Analytics 4 | Track page visits, member signups, popular sections | Free | Non-technical | 🟡 Medium
Security | Cloudflare (Free CDN) | DDoS protection, SSL, fast global delivery | Free tier | Non-technical | 🔴 High
Payments | Razorpay / Paytm | Accept donations, event fees, membership dues online | 1.5–2% per txn | Developer | 🔴 High
Version Control | GitHub | Code repository, collaboration, deployment automation | Free | Developer | 🔴 High
CI/CD | GitHub Actions | Auto-deploy on code push; test automation | Free | Developer | 🟡 Medium

## 👤 Member Portal
MEMBER PORTAL — COMPLETE FEATURE SPECIFICATION
Module | Feature | Description | User Role | Phase | Priority
Registration & Auth | Member Signup | Register with name, mobile, email, city, gotra, family code | Public | Phase 3 | 🔴 High
Registration & Auth | OTP Verification | Verify mobile via SMS OTP before account activation | Public | Phase 3 | 🔴 High
Registration & Auth | Email Verification | Verify email for account security | Public | Phase 3 | 🔴 High
Registration & Auth | Google / Facebook Login | Social login option for faster onboarding | Public | Phase 3 | 🟡 Medium
Registration & Auth | Admin Approval Flow | New registrations need admin review before listing | Admin | Phase 3 | 🔴 High
Registration & Auth | Password Reset | Forgot password flow via OTP or email link | Member | Phase 3 | 🔴 High
Member Profile | Basic Profile | Name, photo, DOB, gender, gotra, native city/village | Member | Phase 3 | 🔴 High
Member Profile | Contact Details | Phone, email, WhatsApp — with privacy settings | Member | Phase 3 | 🔴 High
Member Profile | Address Details | Current city, native place, area/ward, pin code | Member | Phase 3 | 🔴 High
Member Profile | Professional Details | Occupation, business name, industry, designation | Member | Phase 3 | 🔴 High
Member Profile | Educational Details | Highest qualification, college, graduation year | Member | Phase 3 | 🟡 Medium
Member Profile | Profile Photo Upload | Upload photo with cropping tool; moderated | Member | Phase 3 | 🔴 High
Member Profile | Privacy Controls | Choose: public / members-only / private for each field | Member | Phase 3 | 🔴 High
Member Profile | Verified Badge | Admin can mark profiles as verified | Admin | Phase 3 | 🟡 Medium
Member Directory | Search by Name | Full-text search by first name, last name, family name | Member | Phase 3 | 🔴 High
Member Directory | Filter by City | Filter directory by current city or native village | Member | Phase 3 | 🔴 High
Member Directory | Filter by Gotra | Browse members by gotra/clan | Member | Phase 3 | 🟡 Medium
Member Directory | Filter by Profession | Find doctors, lawyers, engineers etc. in samaj | Member | Phase 3 | 🟡 Medium
Member Directory | Browse Alphabetically | A–Z listing with quick jump nav | Member | Phase 3 | 🟡 Medium
Member Directory | Member Count Badge | Show total registered members on homepage | Public | Phase 3 | 🔴 High
Family Module | Family Head Registration | Register as head of family with family code | Member | Phase 3 | 🔴 High
Family Module | Add Family Members | Add spouse, children, parents to family profile | Member | Phase 3 | 🔴 High
Family Module | Family Tree View | Visual tree showing 3 generations | Member | Phase 4 | 🟡 Medium
Family Module | Link Existing Members | Link already-registered members to your family | Member | Phase 3 | 🟡 Medium
Family Module | Family Directory | Browse families; see family tree of other members | Member | Phase 3 | 🟡 Medium
Communication | Member Messaging | Send direct message to another member (moderated) | Member | Phase 4 | 🟡 Medium
Communication | Event Announcements | Receive event alerts via SMS/email/WhatsApp | Member | Phase 3 | 🔴 High
Communication | Samaj Notices Board | Read official notices from committee | Member | Phase 3 | 🔴 High
Donations & Fees | Online Donation | Donate to samaj trust via Razorpay | Member/Public | Phase 3 | 🔴 High
Donations & Fees | Membership Fee | Pay annual membership online | Member | Phase 3 | 🟡 Medium
Donations & Fees | Event Registration Fee | Pay for ticketed events online | Member | Phase 3 | 🟡 Medium
Donations & Fees | Donation Receipt | Auto-generate PDF receipt for tax purposes | Member | Phase 3 | 🟡 Medium
Admin Panel | Member Management | Approve, reject, edit, deactivate member accounts | Admin | Phase 3 | 🔴 High
Admin Panel | Content Management | Post news, notices, gallery, events from backend | Admin | Phase 3 | 🔴 High
Admin Panel | Dashboard Analytics | Total members, recent signups, active users, top pages | Admin | Phase 4 | 🟡 Medium
Admin Panel | Role Management | Assign roles: Super Admin, City Admin, Moderator | Admin | Phase 3 | 🟡 Medium
Admin Panel | Export Member Data | Export directory as CSV/Excel for committee use | Admin | Phase 4 | 🟡 Medium

## 🏠 Family Reg.
FAMILY REGISTRATION — FORM SPEC & DATA FIELDS
# | Field Name | Description / Instructions | Input Type | Required? | Visibility | Section
Family Identification
1 | Family Code (Auto) | System-generated unique family ID (e.g. TS-2024-0042) | Auto-generated | Yes | Admin only | Family ID
2 | Family / Surname | Primary family surname used in samaj | Text | Yes | Public | Family ID
3 | Gotra | Gotra / clan of the family (e.g. Kashyap, Bharadwaj) | Dropdown | Yes | Members | Family ID
4 | Native Village / Town | Original native place of family roots | Text | Yes | Members | Family ID
5 | Current City | City where family currently resides | Text + Map pin | Yes | Members | Family ID
Head of Family
6 | Head's Full Name | Full name of the head of family | Text | Yes | Public | Head of Family
7 | Head's Photo | Profile photo of head of family | Image upload | No | Members | Head of Family
8 | Head's DOB | Date of birth | Date picker | Yes | Members | Head of Family
9 | Head's Mobile | Mobile number (primary contact) | Phone + OTP | Yes | Members | Head of Family
10 | Head's WhatsApp | WhatsApp number (if different) | Phone | No | Members | Head of Family
11 | Head's Email | Email address | Email | No | Members | Head of Family
12 | Head's Occupation | Job / Business / Profession | Text | No | Members | Head of Family
Spouse
13 | Spouse Full Name | Full name of spouse | Text | No | Members | Spouse
14 | Spouse DOB | Date of birth | Date picker | No | Members | Spouse
15 | Spouse's Maiden Surname | Original family name before marriage | Text | No | Members | Spouse
16 | Spouse's Gotra | Gotra of spouse's original family | Dropdown | No | Members | Spouse
17 | Spouse Occupation | Job / Business / Profession | Text | No | Members | Spouse
Children
18 | Child 1 — Name | Full name of first child | Text | No | Members | Children
19 | Child 1 — DOB | Date of birth | Date picker | No | Members | Children
20 | Child 1 — Gender | Gender | Dropdown (M/F/Other) | No | Members | Children
21 | Child 1 — Education | Current school / college / qualification | Text | No | Members | Children
22 | Child 1 — Marital Status | Single / Married / Engaged | Dropdown | No | Members | Children
23 | Child 2–N | Repeat fields for additional children | Repeating group | No | Members | Children
Address & Location
24 | Full Address | House no., street, area | Textarea | Yes | Members | Address
25 | City | Current city of residence | Text | Yes | Members | Address
26 | State | State | Dropdown | Yes | Members | Address
27 | Pincode | Postal code | Number | Yes | Members | Address
28 | Location on Map | Pin location for directory map view | Map picker | No | Members | Address
Other Details
29 | Blood Groups | Blood groups of family members (comma separated) | Text / Multi-select | No | Members | Other
30 | Any Special Skills | E.g. Medical, Legal, Teaching — visible in expert directory | Tags | No | Members | Other
31 | Business Name | If family runs a business — name for trade directory | Text | No | Members | Other
32 | Anniversary Date | Wedding anniversary date for samaj greetings | Date | No | Admin only | Other
33 | Membership Since | Year family joined samaj | Year picker | No | Admin | Other
34 | Notes / Remarks | Admin notes about the family | Textarea | No | Admin only | Admin

## 🏪 Trade Directory
TRADE & BUSINESS DIRECTORY — FEATURE SPEC
Module | Feature | Description | User Role | Phase | Priority
Listing Creation | List a Business | Member adds business: name, category, description, location | Member | Phase 3 | 🔴 High
Listing Creation | Business Categories | Jewellery, Goldsmith, Finance, IT, Medical, Real Estate, Retail, etc. | Admin Setup | Phase 3 | 🔴 High
Listing Creation | Business Logo Upload | Upload company logo or shop photo | Member | Phase 3 | 🟡 Medium
Listing Creation | Multiple Photos | Upload up to 5 photos of shop/product/work | Member | Phase 4 | 🟢 Low
Listing Creation | Contact Info | Phone, WhatsApp, email, website link | Member | Phase 3 | 🔴 High
Listing Creation | Google Maps Pin | Pin exact location on map | Member | Phase 3 | 🟡 Medium
Listing Creation | Operating Hours | Business hours & days | Member | Phase 3 | 🟢 Low
Listing Creation | Services Offered | Tags for services: Gold, Silver, Diamonds, Bullion, etc. | Member | Phase 3 | 🟡 Medium
Listing Creation | GST / License Info | Optional: GST number, trade license for credibility | Member | Phase 4 | 🟢 Low
Search & Browse | Search by Name | Search directory by business name | All | Phase 3 | 🔴 High
Search & Browse | Filter by Category | Filter: Jeweller, Retailer, Professional, Service etc. | All | Phase 3 | 🔴 High
Search & Browse | Filter by City | Show businesses in selected city | All | Phase 3 | 🔴 High
Search & Browse | Nearby Businesses | Show businesses near user's current location | Members | Phase 4 | 🟡 Medium
Search & Browse | Verified Listings | Filter to show only admin-verified businesses | All | Phase 4 | 🟡 Medium
Search & Browse | Featured Listings | Highlighted/promoted listings for sponsors or top members | Admin | Phase 4 | 🟢 Low
Reviews & Trust | Member Reviews | Community members leave ratings for businesses | Members | Phase 4 | 🟡 Medium
Reviews & Trust | Verified Buyer Badge | Mark reviews from real community members | Admin | Phase 4 | 🟡 Medium
Reviews & Trust | Admin Moderation | Admin can remove inappropriate reviews | Admin | Phase 4 | 🟡 Medium
Admin | Approve Listings | Admin reviews & approves before going live | Admin | Phase 3 | 🔴 High
Admin | Feature/Boost Listing | Mark a listing as featured on homepage | Admin | Phase 4 | 🟢 Low
Admin | Analytics per Listing | Views, clicks, WhatsApp taps per business listing | Admin | Phase 4 | 🟢 Low
Special Categories | Jewellery Specialists | Sub-category for gold/silver/diamond craftsmen | Admin | Phase 3 | 🔴 High
Special Categories | Bullion / Commodity | Traders dealing in gold/silver bullion | Admin | Phase 3 | 🟡 Medium
Special Categories | Professional Services | CAs, Lawyers, Doctors from Soni samaj | Admin | Phase 3 | 🟡 Medium
Special Categories | Real Estate | Property dealers, builders from community | Admin | Phase 3 | 🟡 Medium
Special Categories | Exports & Manufacturing | Exporters in diamond, textiles from Surat | Admin | Phase 3 | 🟡 Medium

## 🎓 Study Alignment
EDUCATION & STUDY ALIGNMENT — FEATURE SPEC
Module | Feature | Description | User Role | Phase | Priority
Scholarships | Scholarship Listings | Post available scholarships from samaj trust & external bodies | Admin | Phase 3 | 🔴 High
Scholarships | Scholarship Application | Students apply online; upload marksheets, income proof | Members | Phase 3 | 🔴 High
Scholarships | Eligibility Criteria | Set minimum % marks, income limit, class filters | Admin | Phase 3 | 🔴 High
Scholarships | Application Tracking | Students track application status: Pending/Approved/Rejected | Members | Phase 3 | 🔴 High
Scholarships | Past Scholarship Recipients | List of scholarship winners per year (with consent) | Admin | Phase 4 | 🟡 Medium
Scholarships | Sponsor a Scholarship | Members/businesses can donate to fund scholarships | Member/Donor | Phase 4 | 🟡 Medium
Study Groups | Online Study Groups | Create/join study groups by subject, board, class | Members | Phase 4 | 🟡 Medium
Study Groups | Group Chat / Forum | Discussion thread for each study group | Members | Phase 4 | 🟡 Medium
Study Groups | Share Notes & Resources | Upload PDFs, notes, past papers in study group | Members | Phase 4 | 🟡 Medium
Tutors & Coaching | Tutor Directory | Community members offering tutoring list themselves | Members | Phase 3 | 🟡 Medium
Tutors & Coaching | Filter by Subject | Search tutors by subject: Maths, Science, Commerce etc. | All | Phase 3 | 🟡 Medium
Tutors & Coaching | Coaching Centre Listings | Community-owned coaching centres in samaj | Members | Phase 3 | 🟡 Medium
Tutors & Coaching | Free Tuition Programme | Admin posts free tuition sessions for underprivileged | Admin | Phase 3 | 🟡 Medium
Career Guidance | Career Counselling Listings | Members who offer career counselling advertise here | Members | Phase 4 | 🟢 Low
Career Guidance | Mentorship Board | Senior professionals offer mentorship to students | Members | Phase 4 | 🟡 Medium
Career Guidance | Job Board for Students | Internships, part-time jobs posted by community businesses | Members | Phase 4 | 🟡 Medium
Career Guidance | Success Stories | Feature stories of community members who excelled academically | Admin | Phase 4 | 🟢 Low
Exam & Results | Board Exam Results | Post Class 10/12 toppers from Soni samaj | Admin | Phase 4 | 🟡 Medium
Exam & Results | Merit List | Annual merit list of top students | Admin | Phase 4 | 🟡 Medium
Exam & Results | Competitive Exam Support | Resources for JEE, NEET, UPSC, GPSC, CLAT | Admin | Phase 4 | 🟢 Low
Awareness | Government Scheme Alerts | Post education schemes from Gujarat govt for community | Admin | Phase 3 | 🟡 Medium
Awareness | Samaj Book Fund | Members donate books; request books through portal | Members | Phase 4 | 🟢 Low

## 🏫 School Section
SCHOOL SECTION — FEATURE SPEC
Module | Feature | Description | User Role | Phase | Priority
School Listings | Add School | List a school run by / recommended by community members | Admin/Member | Phase 3 | 🔴 High
School Listings | School Details | Name, address, board (CBSE/GSEB/ICSE), type, fees range | Admin/Member | Phase 3 | 🔴 High
School Listings | School Photo | Upload school building / facility photos | Admin/Member | Phase 3 | 🟡 Medium
School Listings | Contact & Admission Info | Principal contact, admission helpline, website link | Admin/Member | Phase 3 | 🔴 High
School Listings | Filter by Board | CBSE / GSEB / ICSE / IB filter | All | Phase 3 | 🔴 High
School Listings | Filter by City / Area | Schools near a selected location | All | Phase 3 | 🔴 High
School Listings | Filter by Medium | Gujarati / Hindi / English medium filter | All | Phase 3 | 🔴 High
Admissions | Admission Enquiry Form | Parents submit enquiry for a listed school | Public | Phase 3 | 🟡 Medium
Admissions | Admission Season Alerts | Notify community when schools open admissions | Admin | Phase 3 | 🟡 Medium
Admissions | Documents Checklist | What documents are needed for admission | Admin | Phase 3 | 🟡 Medium
Admissions | Scholarship Eligibility | Link school to samaj scholarship criteria | Admin | Phase 4 | 🟢 Low
Results & Toppers | Class 10 Toppers | Annual list of Class 10 board toppers from samaj | Admin | Phase 4 | 🟡 Medium
Results & Toppers | Class 12 Toppers | Annual list of Class 12 board toppers from samaj | Admin | Phase 4 | 🟡 Medium
Results & Toppers | Award Ceremony Integration | Link results to annual samaj felicitation event | Admin | Phase 4 | 🟢 Low
Samaj Schools | Samaj-Run Schools | Highlight schools owned/managed by Tragad Soni samaj | Admin | Phase 3 | 🔴 High
Samaj Schools | School Annual Report | Upload annual report of samaj schools | Admin | Phase 4 | 🟡 Medium
Samaj Schools | Fee Assistance | Apply for fee assistance from samaj for samaj schools | Members | Phase 3 | 🟡 Medium
Teachers | Community Teacher Directory | Teachers from Tragad Soni community register here | Members | Phase 3 | 🟡 Medium
Teachers | Subject-wise Search | Find teachers by subject: Maths, English, Science etc. | All | Phase 3 | 🟡 Medium
Teachers | Private Tuition Request | Post tuition requirement; get matched with teachers | Members | Phase 4 | 🟡 Medium

## 🏥 Healthcare
HEALTHCARE ALIGNMENT — FEATURE SPEC
Module | Feature | Description | User Role | Phase | Priority
Doctor Directory | Doctor Listings | List doctors from Tragad Soni community by speciality | Admin/Member | Phase 3 | 🔴 High
Doctor Directory | Speciality Filter | Filter by General, Cardiologist, Ortho, Gynaec, Dentist etc. | All | Phase 3 | 🔴 High
Doctor Directory | City / Area Filter | Find doctors near your city or locality | All | Phase 3 | 🔴 High
Doctor Directory | Clinic / Hospital Info | Clinic name, address, timings, OPD schedule | Member | Phase 3 | 🔴 High
Doctor Directory | Online Appointment | Book appointment directly via WhatsApp/phone link | All | Phase 4 | 🟡 Medium
Doctor Directory | Free Consultation Flag | Doctor marks if they offer free consult to samaj members | Member | Phase 3 | 🟡 Medium
Hospital & Clinics | Hospital Listings | Hospitals run by or preferred by community members | Admin | Phase 3 | 🟡 Medium
Hospital & Clinics | Samaj Discount Badge | Hospitals offering discounts to Tragad Soni members | Admin | Phase 3 | 🟡 Medium
Hospital & Clinics | Blood Bank Tie-up | Partner blood banks; request blood group | Admin | Phase 3 | 🟡 Medium
Blood Donors | Blood Donor Registry | Members register as blood donors with blood group | Members | Phase 3 | 🔴 High
Blood Donors | Emergency Blood Search | Search donors by blood group and city in emergency | All | Phase 3 | 🔴 High
Blood Donors | Notify Donors | Send alert to matching donors when blood is urgently needed | Admin/Auto | Phase 4 | 🟡 Medium
Health Camps | Health Camp Listings | Post upcoming health camps organised by samaj | Admin | Phase 3 | 🔴 High
Health Camps | Camp Registration | Members register for health camps online | Members | Phase 3 | 🟡 Medium
Health Camps | Camp Reports | Upload post-camp reports: no. attended, tests done etc. | Admin | Phase 4 | 🟢 Low
Health Camps | Eye / Dental / General | Tag camps by type: eye, dental, diabetes, BP etc. | Admin | Phase 3 | 🟡 Medium
Wellness | Health Tips Articles | Post health articles relevant to community demographics | Admin | Phase 4 | 🟢 Low
Wellness | Ayurveda / Traditional | Feature Ayurvedic practitioners from community | Members | Phase 4 | 🟢 Low
Wellness | Mental Health Resources | Post helplines, counsellors, mental wellness info | Admin | Phase 4 | 🟡 Medium
Insurance & Aid | Medical Aid Fund | Apply for medical financial aid from samaj trust | Members | Phase 3 | 🔴 High
Insurance & Aid | Community Health Insurance | Post group health insurance scheme for members | Admin | Phase 4 | 🟡 Medium
Insurance & Aid | Aid Application Status | Track medical aid application online | Members | Phase 4 | 🟡 Medium

## 💍 Matrimony
MATRIMONY SECTION — FEATURE SPEC & PROFILE FIELDS
MODULE FEATURES
# | Feature | Description | User Role | Phase | Privacy Level | Priority
1 | Create Matrimony Profile | Separate matrimony profile (not main member profile) | Member | Phase 3 | 🔒 Members Only | 🔴 High
2 | Profile Activation Toggle | Member can show/hide matrimony profile anytime | Member | Phase 3 | 🔒 Members Only | 🔴 High
3 | Browse Profiles | Browse opposite gender profiles with privacy controls | Member | Phase 3 | 🔒 Members Only | 🔴 High
4 | Advanced Match Filters | Filter: age, city, gotra, education, profession, height | Member | Phase 3 | 🔒 Members Only | 🔴 High
5 | Gotra Check / Block | Automatically warn or block same-gotra matches | System | Phase 3 | Automatic | 🔴 High
6 | Express Interest | Send anonymous interest; revealed only if mutual | Member | Phase 3 | 🔒 Members Only | 🔴 High
7 | Contact Reveal on Mutual Interest | Contact details shared only after both parties agree | System | Phase 3 | Controlled | 🔴 High
8 | Profile Photo with Privacy | Photo blurred by default; visible only to interested members | Member | Phase 3 | 🔒 Members Only | 🔴 High
9 | Horoscope Upload | Upload kundali PDF; visible to interested matches | Member | Phase 4 | 🔒 Members Only | 🟡 Medium
10 | Shortlist Profiles | Save profiles of interest in private shortlist | Member | Phase 3 | Private | 🟡 Medium
11 | Admin Moderation | Admin reviews all new matrimony profiles before going live | Admin | Phase 3 | Admin Only | 🔴 High
12 | Report Inappropriate Profile | Flag fake or inappropriate profiles | Member | Phase 3 | Anonymous | 🔴 High
13 | Success Stories | Couples who matched via portal can share story (optional) | Member | Phase 4 | Public | 🟢 Low
14 | Parent / Guardian Access | Parents can manage child's profile with consent | Member | Phase 4 | Members Only | 🟡 Medium
15 | Premium Match (Future) | Featured profiles, priority listing for active seekers | Admin | Phase 5 | Members Only | 🟢 Low
MATRIMONY PROFILE FIELDS
# | Field | Description | Input Type | Required? | Visibility | Section
Personal
1 | Display Name | First name or chosen name for profile (no full surname for privacy) | Text | Yes | Members | Personal
2 | Profile ID | System ID e.g. TSM-0087 | Auto | Yes | Public | Personal
3 | Gender | Male / Female | Dropdown | Yes | Members | Personal
4 | Date of Birth | DOB for age calculation | Date | Yes | Members | Personal
5 | Height | In feet & inches | Dropdown | Yes | Members | Personal
6 | Complexion | Fair / Wheatish / Dark — optional | Dropdown | No | Members | Personal
7 | Manglik Status | Manglik / Non-Manglik / Partial | Dropdown | No | Members | Personal
8 | Physical Disability | Any disability — optional, private | Dropdown | No | Members (blurred) | Personal
Religious & Family
9 | Gotra | Gotra of the candidate | Dropdown | Yes | Members | Religious
10 | Native City/Village | Ancestral hometown | Text | Yes | Members | Religious
11 | Religious Views | Orthodox / Moderate / Liberal | Dropdown | No | Members | Religious
12 | Diet | Vegetarian / Non-vegetarian | Dropdown | Yes | Members | Religious
13 | Family Type | Joint Family / Nuclear | Dropdown | No | Members | Family
14 | Father's Occupation | Father's profession | Text | No | Members | Family
15 | Mother's Occupation | Mother's profession | Text | No | Members | Family
16 | No. of Siblings | Number of brothers & sisters | Number | No | Members | Family
Education & Career
17 | Highest Education | 10th / 12th / Diploma / Graduate / PG / PhD | Dropdown | Yes | Members | Education
18 | Field of Study | E.g. Commerce, Engineering, Medical, Arts | Text | No | Members | Education
19 | College / University | Name of college attended | Text | No | Members | Education
20 | Occupation | Employed / Self-employed / Business / Student | Dropdown | Yes | Members | Career
21 | Job Profile / Business | Job title or business type | Text | No | Members | Career
22 | Annual Income | Income slab (range, not exact) | Dropdown | No | Members | Career
23 | Work City | Current city of work | Text | Yes | Members | Career
Partner Preferences
24 | Preferred Age Range | Min-max age of preferred partner | Range slider | Yes | Members | Preferences
25 | Preferred Education | Minimum education level | Dropdown | No | Members | Preferences
26 | Preferred City | Open to: same city / any city / specific city | Multi-select | No | Members | Preferences
27 | Preferred Gotra | Accepted gotras (excluding own) | Multi-select | No | Members | Preferences
28 | Preferred Diet | Vegetarian only / Any | Dropdown | No | Members | Preferences
29 | About Partner | Free text about ideal partner | Textarea | No | Members | Preferences
Media & Contact
30 | Profile Photo | 1 photo (blurred to non-interested members) | Image upload | No | Controlled | Media
31 | Horoscope / Kundali | PDF upload of kundali | File upload | No | Interest Only | Media
32 | Contact Number | Mobile (shared only on mutual interest) | Phone | Yes | Interest Only | Contact
33 | Contact Person | Name of person to contact (self/parent) | Text | Yes | Interest Only | Contact
34 | WhatsApp (Optional) | WhatsApp for conversation after match | Phone | No | Interest Only | Contact

## 📅 Phase Detail
TRAGAD SONI — DETAILED TASK TRACKER (ALL PHASES)
Phase | Task | Detail Notes | Start Wk | End Wk | Owner | Dependency | Status | Est. Hours
P1 | Domain Registration | Register .org and .com, setup DNS and professional emails | Wk 1 | Wk 1 | Admin | None | ⬜ To Do | 4
P1 | Hosting Setup | Buy VPS/shared hosting, configure server, SSL certificate | Wk 1 | Wk 1 | Developer | Domain | ⬜ To Do | 6
P1 | Feature Survey | WhatsApp poll in samaj groups about desired features | Wk 1 | Wk 1 | Coordinator | None | ⬜ To Do | 8
P1 | Tech Stack Decision | Finalize WordPress vs Custom — prepare options doc | Wk 2 | Wk 2 | Developer | Survey | ⬜ To Do | 6
P1 | Budget Estimation | Estimate development, hosting, design costs | Wk 2 | Wk 2 | Trustee | Tech Decision | ⬜ To Do | 5
P2 | Sitemap Finalisation | Complete sitemap sign-off with committee | Wk 3 | Wk 3 | UX Designer | P1 Done | ⬜ To Do | 8
P2 | Wireframe — Homepage | Mobile + desktop wireframe for homepage | Wk 3 | Wk 3 | UX Designer | Sitemap | ⬜ To Do | 10
P2 | Wireframe — Member Portal | Login, profile, directory wireframes | Wk 3 | Wk 4 | UX Designer | Sitemap | ⬜ To Do | 16
P2 | Wireframe — Matrimony | Matrimony browse and profile wireframes | Wk 4 | Wk 4 | UX Designer | Sitemap | ⬜ To Do | 10
P2 | Logo & Brand Design | Logo + colour palette + typography system | Wk 4 | Wk 4 | Designer | Sitemap | ⬜ To Do | 16
P2 | Committee Review | Present designs to committee for approval | Wk 5 | Wk 5 | Project Lead | All Designs | ⬜ To Do | 4
P3 | Dev Environment Setup | Git repo, CI/CD, local dev, staging server | Wk 6 | Wk 6 | Developer | P2 Done | ⬜ To Do | 8
P3 | Homepage Development | Hero, stats, events preview, news, gallery preview | Wk 6 | Wk 7 | Developer | Setup | ⬜ To Do | 24
P3 | Member Auth System | Registration, OTP, login, password reset | Wk 7 | Wk 8 | Developer | Homepage | ⬜ To Do | 32
P3 | Member Profile & Directory | Profile CRUD, search, filters, privacy | Wk 8 | Wk 9 | Developer | Auth | ⬜ To Do | 40
P3 | Family Registration Module | Family head, members, tree structure | Wk 9 | Wk 9 | Developer | Member Profile | ⬜ To Do | 32
P3 | Events Calendar | Create, display, RSVP, reminders for events | Wk 9 | Wk 10 | Developer | Profile | ⬜ To Do | 24
P3 | Gallery Module | Photo albums, upload, lightbox, admin approval | Wk 10 | Wk 10 | Developer | Events | ⬜ To Do | 20
P3 | Trade Directory | Business listings, categories, search, map | Wk 10 | Wk 11 | Developer | Profile | ⬜ To Do | 32
P3 | Education & School Section | Scholarships, tutor directory, school listings | Wk 11 | Wk 11 | Developer | Directory | ⬜ To Do | 28
P3 | Healthcare Module | Doctor directory, blood donors, health camps | Wk 11 | Wk 12 | Developer | Directory | ⬜ To Do | 28
P3 | Matrimony Module | Profile, browse, mutual interest, privacy | Wk 12 | Wk 12 | Developer | Profile | ⬜ To Do | 36
P3 | Donation / Payment | Razorpay integration, receipt generation | Wk 12 | Wk 12 | Developer | Auth | ⬜ To Do | 20
P3 | Admin Panel | Member approval, content CMS, analytics | Wk 12 | Wk 12 | Developer | All modules | ⬜ To Do | 32
P4 | QA — All Pages | Cross-device, cross-browser testing | Wk 13 | Wk 13 | QA | All Modules | ⬜ To Do | 24
P4 | Performance Audit | PageSpeed, image compress, CDN, lazy load | Wk 13 | Wk 14 | Developer | QA | ⬜ To Do | 16
P4 | Security Audit | SSL, data encryption, privacy review | Wk 14 | Wk 14 | Developer | Perf. | ⬜ To Do | 12
P4 | Content Entry | History, trustees, initial members, events | Wk 14 | Wk 14 | Content Team | Security | ⬜ To Do | 20
P4 | Pilot Beta (30 members) | Real user testing, feedback collection | Wk 15 | Wk 15 | Project Lead | Content | ⬜ To Do | 16
P4 | Bug Fixes from Beta | Fix issues raised in pilot | Wk 15 | Wk 15 | Developer | Beta | ⬜ To Do | 20
P5 | Launch Event | Demo at samaj gathering; live walkthrough | Wk 16 | Wk 16 | Trustees | P4 Done | ⬜ To Do | 8
P5 | Social Media Broadcast | WhatsApp + Facebook + Instagram campaign | Wk 16 | Wk 16 | Volunteers | Launch | ⬜ To Do | 6
P5 | Member Onboarding Drive | Registration help across cities | Wk 16 | Wk 18 | Coordinators | Broadcast | ⬜ To Do | 40
P5 | Admin Training | Train admins on CMS, member management | Wk 17 | Wk 17 | Developer | Launch | ⬜ To Do | 8
P5 | Monthly Updates Plan | Editorial calendar for news and events | Ongoing | Ongoing | Admin Team | Training | ⬜ To Do | 4
TOTAL ESTIMATED HOURS | [7 empty] | 0

## 🧭 P1 · Planning
TRAGAD SONI COMMUNITY — P1 · PLANNING | [10 empty] | TRAGAD SONI COMMUNITY — PHASE 1 PLANNING SPRINT
📅 Timeline: Week 1–2 |  |  |  | 🏁 Milestone: M1 — Domain & Hosting Live |  |  |  | desidevloper.com · Milan SNTL 84 |  |  | 📅 Timeline: Week 1–2 · 5 Tasks · ~29 Estimated Hours |  |  |  |  | 🏁 Milestone: M1 — Domain & Hosting Live |  |  | desidevloper.com · Milan SNTL 84
# | Task / Deliverable | Detail Notes | Start | End | Owner | Dependency | Status | Est. Hrs | Priority | Planning Notes | ⚡ WEEK 1 — Discovery & Alignment (Run tasks in parallel from Day 1) |  |  |  |  | ⚙️ WEEK 2 — Decisions & Setup (Hard dependency: Tech decision → Domain)
1 | Define Website Goals | List all features: directory, events, matrimony, donations, news, gallery | Wk 1 | Wk 1 | Trustee Committee | None | ⬜ To Do | 4 | 🔴 High | Prepare a written feature wishlist doc | # | Task / Deliverable | What to Do (Detail) | Start | End | Owner | Dependency | Status | Est. Hrs | Action / Quick-Start Tip
2 | Stakeholder Interviews | Collect input from community leaders, youth group, elderly members | Wk 1 | Wk 1 | Project Lead | None | ⬜ To Do | 8 | 🔴 High | Use Google Form or WhatsApp poll | 1 | Define website goals | Write a feature wishlist doc: directory, events, matrimony, donations, news, gallery. Rank by community impact. | Day 1 | Day 2 | Trustee Committee | None | ⬜ To Do | 4 | Use a simple Google Doc. Share in WhatsApp group for async input before the first committee meeting.
3 | Competitor Research | Review 3–5 similar samaj websites for gap analysis & inspiration | Wk 1 | Wk 1 | Researcher | None | ⬜ To Do | 6 | 🔴 High | Document findings in a comparison sheet | 2 | Stakeholder interviews | Collect input from 3 groups: committee leaders, youth (18–30), elderly (60+). 20-min call each. | Day 1 | Day 3 | Project Lead | None | ⬜ To Do | 8 | Run Day 1–3 in parallel with goal-setting. Prepare 5 questions. Record voice notes on phone.
4 | Tech Stack Decision | Finalise WordPress vs React+Node — prepare options doc for committee | Wk 2 | Wk 2 | Developer | Survey done | ⬜ To Do | 6 | 🔴 High | See ⚙️ Tech Stack sheet for full list | 3 | Competitor research | Review 3–5 samaj websites. Screenshot homepage, member portal, matrimony. Note what's missing. | Day 2 | Day 3 | Researcher | None | ⬜ To Do | 6 | Can be done in 2 hrs. Make a simple table: Site ¦ Features ¦ Gaps ¦ Rating. Share with committee.
5 | Budget Estimation | Estimate dev, hosting, design, maintenance costs (Year 1) | Wk 2 | Wk 2 | Trustee | Tech Decision | ⬜ To Do | 5 | 🔴 High | Include monthly opex + one-time capex | 4 | Tech stack decision | Prepare 1-page options doc: WordPress vs React+Node. Cover cost, skill need, speed, scalability. | Day 7 | Day 8 | Developer | Survey results | ⬜ To Do | 6 | Present to committee Day 7 — aim for same-day decision. Recommendation: WordPress for faster launch.
6 | Domain Registration | Register tragadsoni.org / .com; configure DNS; setup @tragadsoni.org email | Wk 2 | Wk 2 | Admin | Budget OK | ⬜ To Do | 4 | 🔴 High | Zoho Mail free tier for 5 committee emails | 5 | Domain & hosting setup ✅ M1 | Register tragadsoni.org + .com. Configure DNS. Set up Hostinger India hosting. 5 Zoho Mail free emails. | Day 8 | Day 10 | Admin | Tech decision | ⬜ To Do | 5 | Namecheap for domain (~₹900/yr). Hostinger Business (~₹300/mo). SSL auto via Let's Encrypt.
7 | Hosting Setup | Buy VPS/shared hosting; configure server; install SSL certificate | Wk 2 | Wk 2 | Developer | Domain | ⬜ To Do | 6 | 🔴 High | Hostinger India (~₹300/mo) or DigitalOcean ₹900/mo
8 | Feature Priority Matrix | Score features: Impact × Effort; finalize Phase 3–5 scope | Wk 2 | Wk 2 | Project Lead | Interviews | ⬜ To Do | 4 | 🔴 High | Use MoSCoW method with committee | ⚡ FASTEST PATH TO M1 — 10-Day Sprint Sequence
TOTAL ESTIMATED HOURS — P1 · Planning | [7 empty] | 43 | ≈ 5 working days |  | Step | Day | Action | Owner | Output / Deliverable | Time (hrs) | Parallel With | Risk if Delayed | Notes | Done?
[11 empty] | 1 | Day 1 | Send WhatsApp feature poll to all samaj groups | Project Lead | Feature input from 50+ members | 1 | Steps 2 & 3 | Low — can catch up Day 2 | Use Google Forms link. Post in all WhatsApp groups simultaneously | ⬜
[11 empty] | 2 | Day 1–3 | Run 3 stakeholder interviews (committee + youth + elderly) | Project Lead | Interview notes doc, top-10 feature list | 8 | Step 1 | Medium — delays goal doc | 20 min each, voice record. Compile into a 1-page summary by Day 3 | ⬜
[11 empty] | 3 | Day 2–3 | Competitor audit: 3–5 samaj websites | Researcher | Comparison table with gaps & screenshots | 6 | Step 1 & 2 | Low | Can assign to any committee volunteer. 2-hr focused task | ⬜
[11 empty] | 4 | Day 5 | Compile feature wishlist + priority matrix | Trustee Committee | Ranked feature list (Google Doc shared) | 4 | — | High — blocks tech decision | Use MoSCoW method. Present top 10 to committee | ⬜
[11 empty] | 5 | Day 7 | Present tech options doc to committee | Developer | Written tech decision (WP vs custom) | 6 | — | HIGH — blocks hosting setup | 1-pager with recommendation. Aim for same-day sign-off | ⬜
[11 empty] | 6 | Day 8 | Register domain tragadsoni.org + .com | Admin | Domains live, DNS configured | 2 | Step 7 | High — M1 blocker | Namecheap ~₹900/yr. Use auto-renew. Also grab .in as backup | ⬜
[11 empty] | 7 | Day 8–9 | Set up Hostinger hosting + SSL + email | Admin | Hosting live, SSL green, 5 Zoho emails active | 3 | Step 6 | High — M1 blocker | Hostinger Business India plan. Free SSL via Let's Encrypt. Zoho Mail free tier | ⬜
[11 empty] | 8 | Day 10 | M1 sign-off — domain & hosting confirmed live | Project Lead | ✅ M1 Complete — ready for Phase 2 | 1 | — | — | Send confirmation email to all trustees. Screenshot + share in WhatsApp group | ⬜
✅ M1 COMPLETE — Domain & Hosting Live · Tech Stack Decided · Goals Documented → Phase 2 DESIGN begins
LEGEND
🔴 High Priority task
🟡 Medium Priority task
Week 1 task
Week 2 task
✅ Milestone / Done
⬜ Status: To Do

## 🎨 P2 · Design
TRAGAD SONI COMMUNITY — P2 · DESIGN
📅 Timeline: Week 3–5 |  |  |  | 🏁 Milestone: M2 — Designs Approved by Committee |  |  |  | desidevloper.com · Milan SNTL 84
# | Task / Deliverable | Detail Notes | Start | End | Owner | Dependency | Status | Est. Hrs | Priority | Planning Notes
1 | Sitemap Creation | Map all pages: Home, About, Members, Events, Gallery, Contact, all portals | Wk 3 | Wk 3 | UX Designer | P1 Done | ⬜ To Do | 8 | 🔴 High | Include Gujarati page labels
2 | Wireframe — Homepage | Mobile-first wireframe: hero banner, stats, events, news, gallery preview | Wk 3 | Wk 3 | UX Designer | Sitemap | ⬜ To Do | 10 | 🔴 High | Prioritise mobile — 70%+ users on Android
3 | Wireframe — Member Portal | Login, registration, profile page, member directory wireframes | Wk 3 | Wk 4 | UX Designer | Sitemap | ⬜ To Do | 16 | 🔴 High | Show privacy toggle UX clearly
4 | Wireframe — Matrimony | Profile browse, mutual interest, filters, blurred photo UX | Wk 4 | Wk 4 | UX Designer | Sitemap | ⬜ To Do | 10 | 🔴 High | Strict privacy — no full contact visible
5 | Wireframe — Trade Directory | Business listing card, search/filter UI, map view | Wk 4 | Wk 4 | UX Designer | Sitemap | ⬜ To Do | 8 | 🔴 High | Category chips for jewellery, CA, medical etc.
6 | Logo & Brand Identity | Design logo; choose colours & fonts reflecting Soni cultural identity | Wk 4 | Wk 4 | Designer | Sitemap | ⬜ To Do | 16 | 🔴 High | Gold + deep colour palette recommended
7 | Gujarati Language Plan | Plan bilingual UI: Gujarati script + English toggle using i18next | Wk 4 | Wk 5 | Developer | Wireframes | ⬜ To Do | 6 | 🔴 High | Unicode Gujarati — test on Chrome Android
8 | High-Fidelity Mockups | Convert wireframes to full-colour mockups (Figma/Adobe XD) | Wk 5 | Wk 5 | Designer | Wireframes + Logo | ⬜ To Do | 20 | 🔴 High | Cover at least: Home, Profile, Directory, Matrimony
9 | Committee Design Review | Present all designs to samaj committee; collect feedback & sign-off | Wk 5 | Wk 5 | Project Lead | All Designs | ⬜ To Do | 4 | 🔴 High | Get written approval before dev starts
TOTAL ESTIMATED HOURS — P2 · Design | [7 empty] | 98 | ≈ 12 working days

## ⚙️ P3 · Development
TRAGAD SONI COMMUNITY — P3 · DEVELOPMENT
📅 Timeline: Week 6–12 |  |  |  | 🏁 Milestone: M3 — Beta Site Ready for Testing |  |  |  | desidevloper.com · Milan SNTL 84
# | Task / Deliverable | Detail Notes | Start | End | Owner | Dependency | Status | Est. Hrs | Priority | Planning Notes
1 | Dev Environment Setup | Git repo, CI/CD pipeline, local dev, staging server on Vercel/DO | Wk 6 | Wk 6 | Developer | P2 Done | ⬜ To Do | 8 | 🔴 High | Use GitHub Actions for auto-deploy
2 | Homepage Development | Hero, member count, events preview, news feed, gallery preview, donation CTA | Wk 6 | Wk 7 | Developer | Setup | ⬜ To Do | 24 | 🔴 High | Core SEO meta + Open Graph for WhatsApp shares
3 | Member Auth System | Signup, OTP SMS verify, email verify, Google login, password reset | Wk 7 | Wk 8 | Developer | Homepage | ⬜ To Do | 32 | 🔴 High | Firebase Auth or Auth0 free tier
4 | Member Profile & Directory | Profile CRUD, photo upload, search by name/city/gotra, privacy controls | Wk 8 | Wk 9 | Developer | Auth | ⬜ To Do | 40 | 🔴 High | Admin approval flow before profile goes live
5 | Family Registration Module | Family head, add members, link existing members, basic family tree | Wk 9 | Wk 9 | Developer | Profile | ⬜ To Do | 32 | 🔴 High | Auto-generate family code TS-YEAR-XXXX
6 | Events Calendar | Create events, RSVP, reminders via WhatsApp, past events archive | Wk 9 | Wk 10 | Developer | Profile | ⬜ To Do | 24 | 🔴 High | iCal export for Google Calendar sync
7 | Photo & Video Gallery | Albums by event/year, upload by admin, lightbox viewer, lazy load | Wk 10 | Wk 10 | Developer | Events | ⬜ To Do | 20 | 🔴 High | Store on AWS S3 / Cloudflare R2
8 | Trade Directory | Business listings, categories, search, Google Maps pin, contact CTA | Wk 10 | Wk 11 | Developer | Profile | ⬜ To Do | 32 | 🔴 High | Jewellery / Bullion / CA / Medical sub-cats
9 | Education & School Section | Scholarships, applications, tutor directory, school listings | Wk 11 | Wk 11 | Developer | Directory | ⬜ To Do | 28 | 🔴 High | See 🎓 Study Alignment + 🏫 School Section sheets
10 | Healthcare Module | Doctor directory, blood donor registry, emergency search, health camps | Wk 11 | Wk 12 | Developer | Directory | ⬜ To Do | 28 | 🔴 High | Blood group search is HIGH priority feature
11 | Matrimony Module | Privacy-first: blurred photos, mutual interest reveal, gotra block | Wk 12 | Wk 12 | Developer | Profile | ⬜ To Do | 36 | 🔴 High | See 💍 Matrimony sheet for full field spec
12 | Donation / Payment | Razorpay integration, auto PDF receipt for 80G, membership fee | Wk 12 | Wk 12 | Developer | Auth | ⬜ To Do | 20 | 🔴 High | Test with ₹1 live transaction before launch
13 | Admin Panel | Member approval, content CMS, analytics dashboard, role management | Wk 12 | Wk 12 | Developer | All modules | ⬜ To Do | 32 | 🔴 High | 3 roles: Super Admin, City Admin, Moderator
TOTAL ESTIMATED HOURS — P3 · Development | [7 empty] | 356 | ≈ 44 working days

## 🧪 P4 · Testing
TRAGAD SONI COMMUNITY — P4 · TESTING
📅 Timeline: Week 13–15 |  |  |  | 🏁 Milestone: M4 — Launch-Ready (Signed Off) |  |  |  | desidevloper.com · Milan SNTL 84
# | Task / Deliverable | Detail Notes | Start | End | Owner | Dependency | Status | Est. Hrs | Priority | Planning Notes
1 | QA — All Pages | Cross-device (Android/iOS/Desktop), cross-browser (Chrome/Safari/Firefox) | Wk 13 | Wk 13 | QA Tester | All Modules | ⬜ To Do | 24 | 🔴 High | Use BrowserStack for device matrix
2 | Performance Audit | PageSpeed ≥ 80, image compress, CDN, lazy load, minify JS/CSS | Wk 13 | Wk 14 | Developer | QA | ⬜ To Do | 16 | 🔴 High | Target <3s load on 4G mobile in Surat
3 | Security Audit | SSL, HTTPS enforce, data encryption, member data privacy (PDPA/IT Act) | Wk 14 | Wk 14 | Developer | Perf. | ⬜ To Do | 12 | 🔴 High | Cloudflare free tier for DDoS + SSL
4 | Content Entry | Enter: samaj history, trustee profiles, initial 50 member records | Wk 14 | Wk 14 | Content Team | Security | ⬜ To Do | 20 | 🔴 High | Use admin panel CSV import feature
5 | Accessibility Check | Screen reader test, font size, colour contrast for elderly users | Wk 14 | Wk 14 | Developer | Content | ⬜ To Do | 8 | 🔴 High | WCAG 2.1 AA minimum standard
6 | Gujarati UI QA | Test Gujarati script rendering on all pages and devices | Wk 14 | Wk 14 | QA Tester | Content | ⬜ To Do | 6 | 🔴 High | Focus on older Android phones common in samaj
7 | Pilot Beta — 30 Members | Closed beta: recruit 30 diverse members (age mix, city mix) | Wk 15 | Wk 15 | Project Lead | Content | ⬜ To Do | 16 | 🔴 High | Use Google Form to collect structured feedback
8 | Bug Fixes from Beta | Fix all critical + major bugs raised in pilot; re-test | Wk 15 | Wk 15 | Developer | Beta | ⬜ To Do | 20 | 🔴 High | Categorise: Critical / Major / Minor / Nice-to-have
9 | Regression Testing | Full re-test after bug fixes to ensure nothing is broken | Wk 15 | Wk 15 | QA Tester | Bug Fixes | ⬜ To Do | 10 | 🔴 High | Smoke test all core user journeys
10 | Final Sign-Off | Project Lead + Committee approve site for public launch | Wk 15 | Wk 15 | Committee | Regression | ⬜ To Do | 2 | 🔴 High | Written sign-off email from trustee required
TOTAL ESTIMATED HOURS — P4 · Testing | [7 empty] | 134 | ≈ 16 working days

## 🚀 P5 · Launch
TRAGAD SONI COMMUNITY — P5 · LAUNCH
📅 Timeline: Week 16–Ongoing |  |  |  | 🏁 Milestone: M5 — Live & Growing |  |  |  | desidevloper.com · Milan SNTL 84
# | Task / Deliverable | Detail Notes | Start | End | Owner | Dependency | Status | Est. Hrs | Priority | Planning Notes
1 | Official Launch Event | Demo website live at samaj gathering; register first 50 members on stage | Wk 16 | Wk 16 | Trustees | P4 Done | ⬜ To Do | 8 | 🔴 High | Prepare 5-min demo video as backup
2 | WhatsApp Campaign | Broadcast registration link to all community WhatsApp groups | Wk 16 | Wk 16 | Volunteers | Launch | ⬜ To Do | 4 | 🔴 High | Pre-write 3 message variants for different audiences
3 | Social Media Broadcast | Facebook + Instagram campaign; post reel/short video of site walkthrough | Wk 16 | Wk 16 | Volunteers | Launch | ⬜ To Do | 6 | 🔴 High | Target: Tragad Soni groups across Gujarat cities
4 | Member Onboarding Drive | Help elderly members register; appoint city-level coordinators | Wk 16 | Wk 18 | Coordinators | Broadcast | ⬜ To Do | 40 | 🔴 High | Target 500 members in first 60 days
5 | Admin Team Training | Train 3–4 admins: post news, approve members, manage events via CMS | Wk 17 | Wk 17 | Developer | Launch | ⬜ To Do | 8 | 🔴 High | Create 1-page admin cheat sheet (Gujarati + English)
6 | Monthly Content Calendar | Plan monthly: news posts, event notices, gallery updates, notices | Wk 17 | Ongoing | Admin Team | Training | ⬜ To Do | 4 | 🔴 High | Use Google Sheets editorial calendar template
7 | City Coordinator Setup | Appoint & brief one coordinator per major city (Surat, Ahmedabad, Rajkot) | Wk 17 | Wk 18 | Project Lead | Onboarding | ⬜ To Do | 6 | 🔴 High | Provide coordinators with registration help kit
8 | 30-Day Review | Review signups, feedback, errors after first month live | Wk 20 | Wk 20 | Project Lead | Onboarding | ⬜ To Do | 4 | 🔴 High | Set targets: 200 members, 20 business listings
9 | Quarterly Feature Review | Collect member feedback; plan new features every 3 months | Ongoing | Ongoing | Committee | 30-Day Review | ⬜ To Do | 4 | 🔴 High | Run annual samaj feature voting poll
10 | SEO & Google Listing | Submit sitemap to Google Search Console; create Google Business Profile | Wk 16 | Wk 17 | Developer | Launch | ⬜ To Do | 4 | 🔴 High | Target keywords: tragad soni, soni samaj surat
TOTAL ESTIMATED HOURS — P5 · Launch | [7 empty] | 88 | ≈ 11 working days